## Summary
Progress summary
Measure | Value
Total plan tasks
Done
In progress
Cut
Not started
% complete (excluding cut)
Requirements verified in Bagisto (Yes)
Total requirements
Fit level breakdown
Fit level | Count
Built-in
Config
Small code change
Custom code
Note: 'Config / small code' items are counted under Config.

## Gap List
Bagisto gap list - Classy Fashion Hub e-commerce system
Fit levels come from general knowledge of Bagisto, not a code audit. Update column F after checking in the admin panel / demo on Day 1. Yellow cells are for you to fill.
# | Requirement | Report section | Fit level | Notes / what to do | Verified in Bagisto? | Planned day
1 | Customer registration, login, password recovery | 9.1 | Built-in | Use default customer auth; confirm password reset email works | Yes | Day 1
2 | Product catalogue: size, colour, price, images, search, filters | 9.2 | Built-in | Use configurable products for size/colour variants | Yes | Day 1
3 | Deactivate (not delete) discontinued products | 9.2 | Built-in | Use the product status toggle | Yes | Day 1
4 | Cart, checkout, order history | 9.5 | Built-in | Run a full test order on Day 1 | Yes | Day 1
5 | Admin dashboard and sales reports | 9.9 | Built-in | Light customisation; check export options |  | Day 3
6 | Admin vs Worker roles with limited permissions | 9.1 | Config | Create a 'Worker' role in the admin ACL; restrict sensitive pages | Yes | Day 1
7 | Stock quantities per product | 9.3 | Built-in | Set inventory per variant | Yes | Day 1
8 | Low-stock threshold and alert | 9.3 / 9.8 | Small code change | Add threshold field plus admin notice or email |  | Day 2
9 | Custom order statuses (Pending, Confirmed, Paid, Processing, Dispatched, Delivered) | 9.5 / 9.7 | Config / small code | Rename or extend default statuses; update status transitions |  | Day 2
10 | Delivery info at checkout (location, contact, instructions) | 9.7 | Small code change | Add fields at checkout and show in admin order view |  | Day 2
11 | Mobile money payment (MTN / Airtel) | 9.6 | Custom code | Flutterwave or Pesapal payment method; mark Paid only after webhook confirmation; use sandbox |  | Day 2-3
12 | Worker audit trail for stock and order changes | 9.3 / 10.2 | Custom code | Add a Laravel activity-log package recording user and date |  | Day 2
13 | Profit per sale | 9.4 | Small code change | Add cost price to products; compute profit on order items |  | Day 2
14 | Customer notifications on order events | 9.8 | Config | Use built-in order emails; add admin new-order notice |  | Day 3
15 | Branding (name, logo, colours) | 10.1 | Config | Theme tweaks | Partly | Day 1
16 | Mobile-friendly interface | 10.8 | Built-in | Test on a real phone |  | Day 3
17 | Luganda language support (optional) | 10.9 | Config | Add a locale if time allows; first thing to cut |  | Day 3

## 3-Day Plan
3-day build plan
Fill Owner and Status (yellow). Status options: Not started, In progress, Done, Cut.
Day | Task | Gap list # | Owner | Status | Notes
Day 1 | Install Bagisto locally and deploy to a live host |  |  | Done | Bagisto v2.4.12 on PHP 8.3.35; :8000 storefront+admin 200; 143 demo products; live deploy deferred (needs external MySQL for Render)
Day 1 | Create Admin and Worker roles with permissions | 6 |  | Done | Worker role (custom, 19 keys) + worker@classy.local seeded; Pest 3/3 pass: worker 200 dashboard/products/orders, 401 roles/users/config
Day 1 | Rebrand theme (name, logo, colours) | 15 |  | In progress | Name+logo+favicon live (header shows logo). Primary-colour token change + asset rebuild running
Day 1 | Add 15-20 products with sizes, colours, images, fixed prices | 2 |  | Done | 16 fashion products (10 configurable+6 simple, 67 variants) in UGX; category API + search verified; demo products wiped
Day 1 | Place a test order end to end | 4 |  | Done | Pest CheckoutFlowTest 15 assertions: variant cart, COD+flatrate, pending UGX order, history visible
Day 1 | Create Flutterwave / Pesapal sandbox account | 11 |  | In progress | Provider deferred by owner; Day 2 builds sandbox payment method (Flutterwave/Pesapal)
Day 2 | Rename / extend order statuses | 9 |  | Not started
Day 2 | Add delivery fields at checkout and admin view | 10 |  | Not started
Day 2 | Add activity log for stock and order changes | 12 |  | Not started
Day 2 | Add low-stock threshold and alert | 8 |  | Not started
Day 2 | Add cost price field and profit calculation | 13 |  | Not started
Day 2 | Start mobile money payment method (sandbox) | 11 |  | Not started
Day 3 | Finish and test payment flow; Paid only on webhook confirmation | 11 |  | Not started
Day 3 | Test on a phone | 16 |  | Not started
Day 3 | Check reports and admin dashboard | 5 |  | Not started
Day 3 | Check the six SMART objectives and capture screenshots |  |  | Not started
Day 3 | Write user guide and demo script |  |  | Not started

## If Time Slips
What to cut, in order
Order | Cut this | Replace with
1 | Luganda language support | English only; mention as future work
2 | Live mobile money payments | Sandbox/test mode; note production approval as next step
3 | Email notifications | Dashboard-only alerts
Do not cut: roles, activity log, order statuses. They show the report was actually implemented.
Note: live Flutterwave/Pesapal merchant approval can take longer than 3 days; create the sandbox account now.